## Project Status
Epic | Sprint | Story | Acceptance Criterion | Status | Notes/Location
Epic 1: Trace ingestion & 2-tier DAG construction | Sprint 1: Picotron instrumentation | Profiler transformer model using Pytorch Profiler, hook timing events | PyTorch Profiler records all ops with timings; chrome trace exported successfully | ✅ DONE | 01_trace_generation_ipynb.ipynb, 02-trace-generation-fixed.ipynb
Epic 1: Trace ingestion & 2-tier DAG construction | Sprint 1: Picotron instrumentation | Run config sweeps, validate critical-path rank vs analytic ground truth | 3 different model sizes/configs (tiny, small, medium) | ✅ DONE | 02-trace-generation-fixed.ipynb - 3 configs implemented
Epic 1: Trace ingestion & 2-tier DAG construction | Sprint 1: Picotron instrumentation | Build Chakra → NetworkX parser: nodes typed, edges correctly directed | All nodes typed (software + network tiers), edges directed, no bidirectional leakage | ✅ DONE | 02-trace-generation-fixed.ipynb - NetworkX DAG construction
Epic 1: Trace ingestion & 2-tier DAG construction | Sprint 1: Picotron instrumentation | NetworkX → PyG HeteroData conversion | HeteroData loads cleanly into PYG; node/edge feature shapes verified | ✅ DONE | 03_heterogat_fixed.ipynb - PyG conversion implemented
Epic 1: Trace ingestion & 2-tier DAG construction | Sprint 1: Picotron instrumentation | Derive HW proxy features from trace stats | Per-node proxy features (compute ratio, comm/compute ratio) non-zero and normalized | ✅ DONE | 02-trace-generation-fixed.ipynb - features computed
Epic 1: Trace ingestion & 2-tier DAG construction | Sprint 2: Baseline analytical model | 1F1B analytic formula baseline implemented | MSE + ΔT error table ready on held-out graphs | ✅ DONE | model_1f1b.ipynb - 1F1B baseline implemented
Epic 1: Trace ingestion & 2-tier DAG construction | Sprint 2: Baseline analytical model | MLP skeleton on flattened features ready; train/val/test splits defined | MLP trains without error; splits fixed and shared with team | ✅ DONE | model_1f1b.ipynb - MLP baseline + splits
Epic 2: Baseline models | Sprint 3: Non-graph baselines | MLP + XGBoost baselines, hyperparameter sweep done | Table 1 numbers logged — MSE + ΔT accuracy for both models across 3 seeds | 🟡 PARTIAL | model_1f1b.ipynb - MLP done, XGBoost + hyperparameter sweep needed
Epic 2: Baseline models | Sprint 3: Non-graph baselines | Compile Table 1: 1F1B vs MLP vs XGBoost | Table populated, consistent across 3 seeds, ready for GNN comparison | 🟡 PARTIAL | Needs XGBoost completion for full Table 1
Epic 3: HeteroGAT + Directed message passing | Sprint 4: HeteroGAT both variants | Variant A: standard bidirectional HeteroGAT (associational baseline) | 2-layer HeteroGAT trains, loss curves stable, slack predictions visible, attn weights extractable | ✅ DONE | 03_heterogat_fixed.ipynb - bidirectional HeteroGAT implemented
Epic 3: HeteroGAT + Directed message passing | Sprint 4: HeteroGAT both variants | Variant B: directed topological message passing (causal inductive bias) | Messages flow ancestor→descendant only, respects DAG topology, plugs into same training loop | ✅ DONE | 03_heterogat_fixed.ipynb - directed variant implemented
Epic 3: HeteroGAT + Directed message passing | Sprint 4: HeteroGAT both variants | Multi-task heads: predict step time + per-node slack jointly | Both task heads show decreasing val loss across both variants | ✅ DONE | 03_heterogat_fixed.ipynb - multi-task learning implemented
Epic 3: HeteroGAT + Directed message passing | Sprint 4: HeteroGAT both variants | Build perturbation what-if harness: edit node → GNN forward pass → predict ΔT | Given trained GNN + edited graph, returns predicted ΔT. Interface contract agreed by W3 end. | ❌ NOT DONE | Needs dedicated notebook - intervention harness not implemented
Epic 3: HeteroGAT + Directed message passing | Sprint 5: Ablations + interventional eval | Ablation A: directed vs bidirectional — Spearman ρ vs analytic critical path | ρ > 0.7 for directed variant; ΔT error < 5% | 🟡 PARTIAL | Models trained, but systematic ablation study needed
Epic 3: HeteroGAT + Directed message passing | Sprint 5: Ablations + interventional eval | Ablation B: HW proxy tier removed vs full graph — MAE delta | MAE delta documented — positive or negative result both acceptable | ❌ NOT DONE | Ablation study not conducted
Epic 3: HeteroGAT + Directed message passing | Sprint 5: Ablations + interventional eval | Run ΔT what-if eval: compare GNN prediction vs simulator rerun | GNN-predicted ΔT within acceptable error of STAGE re-simulation on ≥10 edited graphs | ❌ NOT DONE | Requires what-if harness completion first
Epic 3: HeteroGAT + Directed message passing | Sprint 5: Ablations + interventional eval | OOD splits: train depth 2–4, test depth 6–8 — MAE degradation table | OOD MAE reported; degradation documented as limitation if > 20% | ❌ NOT DONE | No OOD generalization experiments conducted
Epic 4: GraphRAG optimizer loop (LLM Role 3) | Sprint 6: GraphRAG loop | Serialize causal subgraph → structured LLM prompt with node IDs + slack scores | Prompt template finalized, fits context window, node IDs traceable back to graph | ❌ NOT DONE | GraphRAG components not started
Epic 4: GraphRAG optimizer loop (LLM Role 3) | Sprint 6: GraphRAG loop | Generate NL optimizer suggestions for ≥20 graphs via LLM API | Ranked suggestions (microbatch tuning, stage remapping) returned for each graph | ❌ NOT DONE | LLM integration not started
Epic 4: GraphRAG optimizer loop (LLM Role 3) | Sprint 6: GraphRAG loop | Validate top-3 suggestions: re-run GNN forward pass on counterfactually edited graph | ≥2 of 3 top suggestions reduce predicted ΔT when applied — suggestion accuracy metric logged | ❌ NOT DONE | Depends on GraphRAG completion
Epic 4: GraphRAG optimizer loop (LLM Role 3) | Sprint 6: GraphRAG loop | Recall@1 automated eval: does top suggestion match known bottleneck? | Recall@1 computed across ≥20 graphs, results table ready for paper | ❌ NOT DONE | Depends on GraphRAG completion

## Summary
Metric | Value
Total Stories | 21
Completed | 10
Partial | 3
Not Done | 8
Completion % | 47.6%

## Epic Breakdown
Epic | Status
Epic 1: Trace ingestion & 2-tier DAG construction | 7/7 completed
Epic 2: Baseline models | 0/2 completed
Epic 3: HeteroGAT + Directed message passing | 3/8 completed
Epic 4: GraphRAG optimizer loop (LLM Role 3) | 0/4 completed

## Sprint Breakdown
Sprint | Status
Sprint 1: Picotron instrumentation | 5/5 completed
Sprint 2: Baseline analytical model | 2/2 completed
Sprint 3: Non-graph baselines | 0/2 completed
Sprint 4: HeteroGAT both variants | 3/4 completed
Sprint 5: Ablations + interventional eval | 0/4 completed
Sprint 6: GraphRAG loop | 0/4 completed